## Header
Field | Value
ECIR_ID | ECIR-TEST1
Title | Test ECIR
DateGenerated | 2025-11-08 02:09:25
Originator | Estimator
Reason | Supplier_Change
Plan_Set_Old | v1
Plan_Set_New | v2
Supplier_Old | Green Mountain
Supplier_New | Pliris
Overhead_Pct | 0.15
Profit_Pct | 0.1
DirectCost_Old | 150
DirectCost_New | 340
DirectCost_Variance | 190
Overhead_Old | 22.5
Overhead_New | 51
Overhead_Variance | 28.5
Profit_Old | 17.25
Profit_New | 39.1
Profit_Variance | 21.85
TotalCost_Old | 189.75
TotalCost_New | 430.1
TotalCost_Variance | 240.35
ScheduleImpact | No impact

## Summary
Category | DirectCost_Old | DirectCost_New | DirectCost_Variance | Overhead_Old | Overhead_New | Overhead_Variance | Profit_Old | Profit_New | Profit_Variance | IndirectCost_Variance | Total_Old | Total_New | Total_Variance | DirectCost_Variance_pct | Total_Variance_pct
glulams | 150 | 200 | 50 | 22.5 | 30 | 7.5 | 17.25 | 23 | 5.75 | 13.25 | 189.75 | 253 | 63.25 | 0.33333 | 0.33333
hardware | 0 | 60 | 60 | 0 | 9 | 9 | 0 | 6.9 | 6.9 | 15.9 | 0 | 75.9 | 75.9 | 0 | 0
strapping | 0 | 80 | 80 | 0 | 12 | 12 | 0 | 9.2 | 9.2 | 21.2 | 0 | 101.2 | 101.2 | 0 | 0

## Detail
UIK | Category | Item_Status | Description_Old | Description_New | EngRef_Old | EngRef_New | Quantity_Old | Quantity_New | Quantity_Variance | Quantity_Variance_pct | UnitCost_Old | UnitCost_New | UnitCost_Variance | TotalCost_Old | TotalCost_New | DirectCost_Variance | DirectCost_Variance_pct | Overhead_Old | Overhead_New | Overhead_Variance | Profit_Old | Profit_New | Profit_Variance | IndirectCost_Variance | TotalCostWithOH_Profit_Old | TotalCostWithOH_Profit_New | TotalCostWithOH_Profit_Variance
glulams::Beam 5-1/8x10 | glulams | Deleted | Beam 5-1/8x10 |  | nan |  | 1 | 0 | -1 | -1 | 150 | 0 | -150 | 150 | 0 | -150 | -1 | 22.5 | 0 | -22.5 | 17.25 | 0 | -17.25 | -39.75 | 189.75 | 0 | -189.75
glulams::Beam 5-1/8x12 | glulams | Added |  | Beam 5-1/8x12 |  | Upsize glulam beam per sheet S3.2 | 0 | 1 | 1 | 0 | 0 | 200 | 200 | 0 | 200 | 200 | 0 | 0 | 30 | 30 | 0 | 23 | 23 | 53 | 0 | 253 | 253
hardware::HDU2 hold-down | hardware | Added | HDU2 hold-down | HDU2 hold-down | nan | Add 4 hold-downs per sheet S4.1 | 0 | 4 | 4 | 0 | 15 | 15 | 0 | 0 | 60 | 60 | 0 | 0 | 9 | 9 | 0 | 6.9 | 6.9 | 15.9 | 0 | 75.9 | 75.9
strapping::MSTC strap | strapping | Added | MSTC strap | MSTC strap | nan | Add strapping per sheet S5.0 | 0 | 8 | 8 | 0 | 10 | 10 | 0 | 0 | 80 | 80 | 0 | 0 | 12 | 12 | 0 | 9.2 | 9.2 | 21.2 | 0 | 101.2 | 101.2