## Detailed
Category | Item | Quantity_Before | Quantity_After | Quantity_Variance | Quantity_Variance_pct | UnitCost_Before | UnitCost_After | UnitCost_Variance | TotalCost_Before | TotalCost_After | Cost_Variance | Cost_Variance_pct | EngineeringReference
glulams | Beam 5-1/8x10 | 1 | 0 | -1 | -1 | 150 | 0 | -150 | 150 | 0 | -150 | -1
glulams | Beam 5-1/8x12 | 0 | 1 | 1 | 0 | 0 | 200 | 200 | 0 | 200 | 200 | 0 | Upsize glulam beam per sheet S3.2
hardware | HDU2 hold-down | 0 | 4 | 4 | 0 | 15 | 15 | 0 | 0 | 60 | 60 | 0 | Add 4 hold-downs per sheet S4.1
strapping | MSTC strap | 0 | 8 | 8 | 0 | 10 | 10 | 0 | 0 | 80 | 80 | 0 | Add strapping per sheet S5.0

## Summary
Category | TotalCost_Before | TotalCost_After | Cost_Variance | Cost_Variance_pct
glulams | 150 | 200 | 50 | 0.33333
hardware | 0 | 60 | 60 | 0
strapping | 0 | 80 | 80 | 0