## Detail
Plan Reference | Category | Item Description | Unit | Qty Before | Unit Cost Before | Qty After | Unit Cost After | Engineering Note | Extended Before | Extended After | Dollar Variance | Percent Variance
S3.2 | Glulam | Glulam Beam 5-1/4 x 12 | each | 10 | 150 | 12 | 155 | Beam size increased for load path | 1500 | 1860 | 360 | 24
S3.2 | Hardware | HDU8 Hold-Down Anchor | each | 20 | 8 | 24 | 8.5 | Additional hold-downs per sheet S3.2 | 160 | 204 | 44 | 27.5
S3.5 | Strapping | Simpson MST48 Strap | each | 50 | 3 | 55 | 3.5 | Added strap at roof shear wall per S3.5 | 150 | 192.5 | 42.5 | 28.3333
S4.1 | Hold-down | HDU14 Hold-Down Anchor | each | 15 | 12 | 18 | 12.5 | Increased hold-down capacity per eng. directive | 180 | 225 | 45 | 25

## Summary
Category | Qty_Before | Qty_After | Cost_Before | Cost_After | Dollar_Variance | Percent_Variance
Glulam | 10 | 12 | 1500 | 1860 | 360 | 24
Hardware | 20 | 24 | 160 | 204 | 44 | 27.5
Hold-down | 15 | 18 | 180 | 225 | 45 | 25
Strapping | 50 | 55 | 150 | 192.5 | 42.5 | 28.3333