## Sheet1
# | Phase/Task | Status | Start | Duration | End | Assigned To
1 | Pre-Permit | Not Started | 2025-11-14 | 1 | 2025-11-15
1 | Architecturals Per Customer Selections | Not Started | 2025-11-14 | 1 | 2025-11-15
2 | Design Center Appt Confirmed | Not Started | 2025-11-14 | 1 | 2025-11-15
3 | Preliminary Budget | Not Started | 2025-11-14 | 1 | 2025-11-15
4 | Gather City Permit Requirements/Application | Not Started | 2025-11-14 | 1 | 2025-11-15
5 | Plot Plan | Not Started | 2025-11-14 | 1 | 2025-11-15
6 | Soils Test | Not Started | 2025-11-14 | 1 | 2025-11-15
7 | Engineering (Truss, Shear Wall, Etc.) | Not Started | 2025-11-14 | 1 | 2025-11-15
8 | Engineering Letters (Foundation, Brick Over Wood, Etc) | Not Started | 2025-11-14 | 1 | 2025-11-15
9 | Truss/Joist Boise Design Framer Packet | Not Started | 2025-11-14 | 1 | 2025-11-15
10 | Energy Star Compliance | Not Started | 2025-11-14 | 1 | 2025-11-15
11 | HVAC Design | Not Started | 2025-11-14 | 1 | 2025-11-15
12 | Manual J's | Not Started | 2025-11-14 | 1 | 2025-11-15
13 | Res Check | Not Started | 2025-11-14 | 1 | 2025-11-15
14 | Plumbing Design/Overlay | Not Started | 2025-11-14 | 1 | 2025-11-15
15 | SWPPP Design | Not Started | 2025-11-14 | 1 | 2025-11-15
2 | Permit | Not Started | 2025-11-17 | 9 | 2025-11-26
1 | Issue Purchase Orders | Not Started | 2025-11-17 | 1 | 2025-11-18
2 | Enter Job Into JSM System-Template Specific | Not Started | 2025-11-17 | 1 | 2025-11-18
3 | Permit Preparation Docs | Not Started | 2025-11-18 | 1 | 2025-11-19
4 | Permitting | Not Started | 2025-11-19 | 5 | 2025-11-26
3 | Plumbing Rough | Not Started | 2025-11-18 | 25 | 2025-12-13
1 | Team Meeting/CS Signoff With Customer | Not Started | 2025-11-18 | 1 | 2025-11-19
2 | Lot & Envelope Stake From Surveyor | Not Started | 2025-11-19 | 1 | 2025-11-20
3 | Erosion Control | Not Started | 2025-11-26 | 1 | 2025-11-27
4 | Lot Bench | Not Started | 2025-11-20 | 1 | 2025-11-21
5 | Order Temp Electric Pole | Not Started | 2025-11-26 | 1 | 2025-11-27
6 | City Temp Electric Inspection | Not Started | 2025-11-28 | 1 | 2025-11-29
7 | Order Temp Meter | Not Started | 2025-11-26 | 1 | 2025-11-27
8 | Order Trash Box | Not Started | 2025-11-26 | 1 | 2025-11-27
9 | Order Form Material | Not Started | 2025-11-24 | 1 | 2025-11-25
10 | Set Forms- Form Crew | Not Started | 2025-11-28 | 1 | 2025-11-29
11 | Order Water Meter | Not Started | 2025-11-26 | 1 | 2025-11-27
12 | Window Takeoff | Not Started | 2025-11-21 | 1 | 2025-11-22
13 | Order Brick | Not Started | 2025-11-21 | 1 | 2025-11-22
14 | Order Appliances | Not Started | 2025-11-21 | 1 | 2025-11-22
15 | Order Door/Bath Hardware | Not Started | 2025-11-21 | 1 | 2025-11-22
16 | Form Survey | Not Started | 2025-12-01 | 3 | 2025-12-04
17 | City Form Survey Inspection | Not Started | 2025-12-05 | 1 | 2025-12-06
18 | Drill Piers (If Needed) | Not Started | 2025-12-08 | 1 | 2025-12-09
19 | Deliver Bedding Sand | Not Started | 2025-12-08 | 1 | 2025-12-09
20 | Plumbing Rough | Not Started | 2025-12-09 | 2 | 2025-12-11
21 | Plumbing Rough Inspection | Not Started | 2025-12-12 | 1 | 2025-12-13
4 | Foundation | Not Started | 2025-12-15 | 10 | 2025-12-25
1 | Back Fill Rough | Not Started | 2025-12-15 | 1 | 2025-12-16
2 | Order Sheer Wall HTT Straps | Not Started | 2025-12-15 | 1 | 2025-12-16
3 | Foundation Makeup Crew | Not Started | 2025-12-16 | 1 | 2025-12-17
4 | Foundation Back Out Crew | Not Started | 2025-12-16 | 1 | 2025-12-17
5 | City Foundation Inspetion | Not Started | 2025-12-18 | 1 | 2025-12-19
6 | Engineer Pre-Pour Inspection | Not Started | 2025-12-17 | 1 | 2025-12-18
7 | Pour Foundation | Not Started | 2025-12-19 | 1 | 2025-12-20
8 | Slump Test Engineer | Not Started | 2025-12-19 | 1 | 2025-12-20
9 | Post Pour Survey/ Elevation Cert. | Not Started | 2025-12-22 | 1 | 2025-12-23
10 | Pull Forms | Not Started | 2025-12-24 | 1 | 2025-12-25
11 | Rough Grade | Not Started | 2025-12-23 | 1 | 2025-12-24
5 | Framing | Not Started | 2025-12-24 | 22 | 2026-01-15
1 | Deliver Framing Material | Not Started | 2025-12-24 | 1 | 2025-12-25
2 | Framing Labor | Not Started | 2025-12-25 | 10 | 2026-01-08
3 | Order Truss/Joists | Not Started | 2025-12-25 | 1 | 2025-12-26
4 | Order Decking | Not Started | 2025-12-25 | 1 | 2025-12-26
5 | Order Cornice Material | Not Started | 2025-12-25 | 1 | 2025-12-26
6 | Cornice Labor | Not Started | 2026-01-08 | 4 | 2026-01-14
7 | Deliver Windows | Not Started | 2026-01-08 | 1 | 2026-01-09
8 | Install Windows | Not Started | 2026-01-09 | 1 | 2026-01-10
9 | Order Final Front Door | Not Started | 2026-01-14 | 1 | 2026-01-15
10 | Install Window Protective Coating | Not Started | 2026-01-12 | 1 | 2026-01-13
11 | Frame Trash Haul/Clean | Not Started | 2026-01-14 | 1 | 2026-01-15
6 | Roof & Mechanical Roughs | Not Started | 2026-01-14 | 10 | 2026-01-24
1 | Roof Install | Not Started | 2026-01-14 | 1 | 2026-01-15
2 | Exterior Door Measure | Not Started | 2026-01-14 | 1 | 2026-01-15
3 | Trim Material Walk | Not Started | 2026-01-14 | 1 | 2026-01-15
4 | Plumbing Top Out | Not Started | 2026-01-14 | 3 | 2026-01-17
5 | Install Fireplace(s) | Not Started | 2026-01-14 | 1 | 2026-01-15
6 | HVAC Rough | Not Started | 2026-01-14 | 2 | 2026-01-16
7 | Electrical Rough | Not Started | 2026-01-19 | 2 | 2026-01-21
8 | Set Exterior Doors | Not Started | 2026-01-14 | 1 | 2026-01-15
9 | Low Voltage Rough | Not Started | 2026-01-14 | 1 | 2026-01-15
10 | Polyseal Install | Not Started | 2026-01-21 | 1 | 2026-01-22
11 | Mechanical Trash Haul/Clean | Not Started | 2026-01-21 | 1 | 2026-01-22
12 | Energy Star Poly Inspection | Not Started | 2026-01-22 | 1 | 2026-01-23
13 | Order Lentils | Not Started | 2026-01-22 | 1 | 2026-01-23
14 | Order Brick Sand | Not Started | 2026-01-22 | 1 | 2026-01-23
15 | Order Mortar | Not Started | 2026-01-22 | 1 | 2026-01-23
16 | Cabinet Measure Walk | Not Started | 2026-01-15 | 1 | 2026-01-16
17 | Customer Pre-Sheetorck Meeting | Not Started | 2026-01-22 | 1 | 2026-01-23
18 | Drywall Delivery (5/8 Fire @ Site) | Not Started | 2026-01-22 | 1 | 2026-01-23
19 | Install Z-Flashing | Not Started | 2026-01-22 | 1 | 2026-01-23
20 | Install Lentils For Inspections | Not Started | 2026-01-23 | 1 | 2026-01-24
21 | Drop Brick | Not Started | 2026-01-22 | 1 | 2026-01-23
22 | Deliver Stone | Not Started | 2026-01-22 | 1 | 2026-01-23
7 | City Frame & Rough Inspections | Not Started | 2026-01-22 | 5 | 2026-01-27
1 | City Sheer Wall Inspection | Not Started | 2026-01-22 | 1 | 2026-01-23
2 | City Framing Inspection | Not Started | 2026-01-22 | 1 | 2026-01-23
3 | Engineering Inspection | Not Started | 2026-01-22 | 1 | 2026-01-23
4 | City Mechanical Inspection | Not Started | 2026-01-22 | 1 | 2026-01-23
5 | Install Insulation | Not Started | 2026-01-23 | 1 | 2026-01-24
6 | City Insulation Inspection | Not Started | 2026-01-26 | 1 | 2026-01-27
7 | Energy Star Insulation Inspection | Not Started | 2026-01-26 | 1 | 2026-01-27
8 | Sheetrock & Brick | Not Started | 2026-01-23 | 19 | 2026-02-11
1 | Install Siding | Not Started | 2026-01-27 | 1 | 2026-01-28
2 | Set Exterior/Temp Doors | Not Started | 2026-01-27 | 1 | 2026-01-28
3 | Brick/Stone Labor | Not Started | 2026-01-23 | 7 | 2026-02-03
4 | Hang Sheetrock | Not Started | 2026-01-27 | 2 | 2026-01-29
5 | City Drywall Nail Inspection | Not Started | 2026-01-29 | 1 | 2026-01-30
6 | Tape/Bed/Texture | Not Started | 2026-01-30 | 8 | 2026-02-11
9 | Flatwork & Trim | Not Started | 2026-01-28 | 36 | 2026-03-05
1 | Brick/Drywall Trash Haul/Clean | Not Started | 2026-02-03 | 1 | 2026-02-04
2 | Install Construction Door Locks | Not Started | 2026-01-28 | 1 | 2026-01-29
3 | Install OH Garage Door | Not Started | 2026-02-11 | 1 | 2026-02-12
4 | Exterior Paint | Not Started | 2026-02-12 | 3 | 2026-02-17
5 | Install Naildown Floors | Not Started | 2026-02-11 | 1 | 2026-02-12
6 | Install Stairs | Not Started | 2026-02-12 | 1 | 2026-02-13
7 | Install Cabinets | Not Started | 2026-02-13 | 1 | 2026-02-14
8 | Granite Templates | Not Started | 2026-02-16 | 1 | 2026-02-17
9 | Marble Templates | Not Started | 2026-02-16 | 1 | 2026-02-17
10 | Order Trim Material/Int Door Drop | Not Started | 2026-02-12 | 1 | 2026-02-13
11 | Trim Labor | Not Started | 2026-02-16 | 5 | 2026-02-21
12 | Pre-Paint Interior Clean | Not Started | 2026-02-23 | 1 | 2026-02-24
13 | Trash Haul From Garage/Clean | Not Started | 2026-02-23 | 1 | 2026-02-24
14 | Order Curb Cut For Flatwork | Not Started | 2026-02-04 | 1 | 2026-02-05
15 | Set Flatwork | Not Started | 2026-02-04 | 1 | 2026-02-05
16 | Texture Repair Trip 1 | Not Started | 2026-02-23 | 1 | 2026-02-24
17 | Interior Paint | Not Started | 2026-02-24 | 7 | 2026-03-05
18 | City Flatwork/Approcah Inspection | Not Started | 2026-02-24 | 1 | 2026-02-25
19 | Pour Flatwork | Not Started | 2026-02-25 | 1 | 2026-02-26
20 | Final Grade | Not Started | 2026-02-26 | 1 | 2026-02-27
21 | Install Fencing | Not Started | 2026-02-27 | 1 | 2026-02-28
22 | Final Grade Inspection | Not Started | 2026-02-27 | 1 | 2026-02-28
23 | Final Survey | Not Started | 2026-03-02 | 1 | 2026-03-03
10 | Tops, Trims & Meters | Not Started | 2026-03-05 | 7 | 2026-03-12
1 | Install Floor & Wall Tile | Not Started | 2026-03-05 | 4 | 2026-03-11
2 | Install Granite | Not Started | 2026-03-05 | 1 | 2026-03-06
3 | Install Marble | Not Started | 2026-03-05 | 1 | 2026-03-06
4 | Order Shower Glass/Mirror Measure | Not Started | 2026-03-11 | 1 | 2026-03-12
5 | HVAC Trim | Not Started | 2026-03-05 | 1 | 2026-03-06
6 | Electrical Trim | Not Started | 2026-03-05 | 1 | 2026-03-06
7 | Drop Door/Bath Hardware | Not Started | 2026-03-05 | 1 | 2026-03-06
8 | Low Voltage Trim | Not Started | 2026-03-05 | 1 | 2026-03-06
9 | Electrical Meter Release | Not Started | 2026-03-06 | 1 | 2026-03-07
10 | Order Final Electric Meter | Not Started | 2026-03-09 | 1 | 2026-03-10
11 | Electric Meter Installed | Not Started | 2026-03-09 | 1 | 2026-03-10
12 | Order Hot Check Post Meters | Not Started | 2026-03-10 | 1 | 2026-03-11
13 | Gas Meter Release | Not Started | 2026-03-06 | 1 | 2026-03-07
14 | Order Gas Meter | Not Started | 2026-03-09 | 1 | 2026-03-10
15 | Gas Meter Installed | Not Started | 2026-03-09 | 1 | 2026-03-10
16 | HVAC Startup | Not Started | 2026-03-10 | 1 | 2026-03-11
17 | Trash Haul From Garage/Clean | Not Started | 2026-03-06 | 1 | 2026-03-07
11 | Landscape & Carpet | Not Started | 2026-03-03 | 10 | 2026-03-13
1 | Install Irrigation | Not Started | 2026-03-03 | 1 | 2026-03-04
2 | Install Final Front Door | Not Started | 2026-03-06 | 1 | 2026-03-07
3 | City Backflow Inspection | Not Started | 2026-03-04 | 1 | 2026-03-05
4 | Install Appliances | Not Started | 2026-03-10 | 1 | 2026-03-11
5 | Deliver Door/Bath Hardware | Not Started | 2026-03-09 | 1 | 2026-03-10
6 | Install Door/Bath Hardware | Not Started | 2026-03-11 | 1 | 2026-03-12
7 | Install Landscape/Sod | Not Started | 2026-03-04 | 1 | 2026-03-05
8 | Hadwoood Floor Finish/Engineered | Not Started | 2026-03-11 | 1 | 2026-03-12
9 | Install Glass & Mirrors | Not Started | 2026-03-10 | 1 | 2026-03-11
10 | Interior Clean | Not Started | 2026-03-11 | 1 | 2026-03-12
11 | Install Carpet | Not Started | 2026-03-12 | 1 | 2026-03-13
12 | Final & Closing | Not Started | 2026-03-13 | 5 | 2026-03-18
1 | Advise/Check on Loan Lock | Not Started | 2026-03-13 | 1 | 2026-03-14
2 | Final Texture Touchup | Not Started | 2026-03-13 | 1 | 2026-03-14
3 | Final Paint Touchup | Not Started | 2026-03-16 | 1 | 2026-03-17
4 | Blower Door Test Energy Final | Not Started | 2026-03-13 | 1 | 2026-03-14
5 | City Final Inspection | Not Started | 2026-03-13 | 1 | 2026-03-14
6 | Order 442 Final Inspection As Needed | Not Started | 2026-03-13 | 1 | 2026-03-14
7 | Cert of Occupancy City | Not Started | 2026-03-13 | 1 | 2026-03-14
8 | Home Owner Final Walk Through | Not Started | 2026-03-16 | 1 | 2026-03-17
9 | Closing/Funding | Not Started | 2026-03-16 | 1 | 2026-03-17
10 | Rekey Final Locks | Not Started | 2026-03-17 | 1 | 2026-03-18
11 | Owner Delivery Meeting | Not Started | 2026-03-17 | 1 | 2026-03-18